## Sprint 1
|  |  | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Set up GitHub Repository with Git Classroom Invite for our Team | Sravani | 1 | bar: 2025-02-24
Set up the React project and database schema designed for Users and Business Owners | Venkat | 3 | 2025-02-24: 3
Created UI wireframes for home, restaurant, business owner, and admin pages | Tharun | 2 | 2025-02-24: 2
Configured MongoDB and integrated it with Node backend & planned intial UI wireframes | Sravani | 3 | 2025-03-01: 3
Designed the database schema for Admin and Reviews | Tharun | 2 | 2025-03-01: 2
Established node backend with clear folder & designed database schema for restaurants | Dinesh | 3 | 2025-03-04: 3
Designed APIs for Business Owner functionalities | Dinesh | 3 | 2025-03-06: 3
Began designing and implementing APIs for restaurant functionalities | Venkat | 3 | 2025-02-25: 3
Developed Review APIs and Admin APIs | Tharun | 2 | 2025-02-25: 2
Started development of APIs for User functionalities | Sravani | 2 | 2025-03-01: 2
|  | 24 | 18 | 13 | 13 | 13 | 13 | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0

## Sprint 2
|  |  | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Created reusable navigation bar and footer components | Dinesh | 2 | 2025-03-15: 2
Built Restaurant page components and finalized database schema | Tharun | 3 | 2025-03-16: 3
Completed APIs for registration, login, and user profiles | Sravani | 5 | 2025-03-18: 5
Completed the static Home page with restaurant listings | Venkat | 3 | 2025-03-19: 3
Designed schema and APIs for Admin dashboard o identify duplicate listings | Tharun | 4 | 2025-03-20: 4
Developed search APIs for filtering restaurants by zip code | Dinesh | 5 | 2025-03-17: 5
Built the "Add Restaurants" form for Business Owners & photo handling in DB | Venkat | 4 | 2025-03-21: 4
Integrated Google Maps on the homepage & Created APIs for fetching restaurant details by zip code | Sravani | 2 | 2025-03-21: 2
|  | 28 | 28 | 28 | 28 | 28 | 28 | 26 | 23 | 18 | 13 | 10 | 6 | 0 | 0 | 0

## Sprint 3
|  |  | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Integrated "Add Restaurants" API with the form and enabled photo uploads | Venkat | 3 | 2025-03-27: 3
Built a dynamic Review submission form with validation | Sravani | 3 | 2025-03-29: 3
Designed Admin dashboard pages and APIs to identify duplicate listings | Tharun | 5 | 2025-04-04: 5
Completed advanced filtering APIs for restaurant search | Dinesh | 5 | 2025-04-05: 5
Implemented role-based authentication using JWT tokens | Tharun | 5 | 2025-03-28: 5
Developed Edit Restaurant and Delete Restaurant APIs | Venkat | 1 | bar: 2025-03-24
Integrated search filters for date, time, #people and zip code | Dinesh | 3 | 2025-03-27: 3
Created APIs for submitting reviews and linking them to restaurant records | Sravani | 5 | 2025-04-02: 5
Final approval for Edit/Delete features | Sravani | 1 | bar: 2025-04-06
|  | 31 | 30 | 30 | 30 | 27 | 22 | 19 | 19 | 19 | 19 | 14 | 14 | 9 | 4 | 3

## Sprint 4
|  |  | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Integrated Admin dashboard with backend APIs | Sravani | 2 | 2025-04-10: 2
Developed APIs for fetching Business Owners’ restaurant listings, booking & cancelling tables | Tharun | 3 | 2025-04-09: 3
Developed Edit Restaurant and Delete Restaurant pages | Venkat | 5 | 2025-04-15: 5
Implemented backend integration for reviews and authentication | Dinesh | 5 | 2025-04-12: 5
Added input validations for login/registration forms | Dinesh | 2 | 2025-04-11: 2
Enabled dynamic viewing of restaurant details with reviews and aggregated ratings | Sravani | 5 | 2025-04-16: 5
Enhanced Add/Edit Restaurant forms with validations and error handling | Venkat | 2 | 2025-04-19: 2
Integrated Admin functionalities with the frontend | Tharun | 4 | 2025-04-15: 4
|  | 28 | 28 | 28 | 25 | 23 | 21 | 16 | 16 | 16 | 7 | 2 | 2 | 2 | 0 | 0

## Sprint 5
|  |  | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Implemented Analytical Dashboard for Admin | Tharun | 3 | 2025-04-21: 3
Integrated table booking and cancellation APIs into the UI | Sravani | 3 | 2025-04-23: 3
Completed validation for search inputs | Dinesh | 4 | 2025-04-29: 4
Finalized Update Restaurant API for Business Owners | Venkat | 5 | 2025-04-26: 5
Deployed backend to AWS with auto-scaling EC2 instances and MongoDB | Dinesh | 4 | 2025-04-30: 4
Polished Review submission form and finalized app design | Sravani | 5 | 2025-04-30: 5
fixed UI/UX identified issues | Tharun | 5 | 2025-05-02: 5
Enabled Business Owners to upload/update restaurant photos | Venkat | 3 | 2025-04-28: 3
|  | 32 | 29 | 29 | 26 | 26 | 26 | 21 | 21 | 18 | 14 | 5 | 5 | 0 | 0 | 0

## Sprint 6
|  |  | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10
Task | Names | Story Points | Day 1 | Day 2 | Day 3 | Day. 4 | Day 5 | Day 6
Improved the app responsiveness for desktop devices, ensuring compatibility across screen sizes | Venkat | 4 | 4
Deployed frontend to AWS S3 and completed deployment architecture diagrams | Sravani | 4 |  |  |  | 4
Prepared a component diagram | Dinesh | 4 |  | 4
Validated backend deployment and prepared for final demo | Tharun | 4 |  |  |  |  | 4
|  | 16 | 12 | 8 | 8 | 4 | 0 | 0